## Programme_Milestones
Milestone_ID | Workstream | Milestone_Name | Region | Priority | Planned_Start | Planned_End | Actual_Start | Actual_End | Status | Days_Variance | Completion_% | Owner | Notes
MS-1001 | Mains Replacement | Site Survey Complete | Merseyside | High | 2026-05-11 | 2026-06-29 | 2026-05-15 |  | On Track | -3 | 54% | Sarah Mitchell
MS-1002 | Mains Replacement | Ground Investigation | Cheshire | Low | 2026-04-30 | 2026-07-11 | 2026-05-04 |  | On Track | 5 | 74% | Tom Davies
MS-1003 | Mains Replacement | Design Approved | Merseyside | Medium | 2026-02-09 | 2026-04-10 | 2026-02-13 | 2026-04-14 | Complete | 4 | 100% | Tom Davies
MS-1004 | Mains Replacement | Procurement Complete | Cumbria | High | 2026-03-21 | 2026-05-24 | 2026-03-28 |  | Overdue | 21 | 88% | Laura Bennett
MS-1005 | Mains Replacement | Pipe Installation Phase 1 | Cheshire | Medium | 2026-02-13 | 2026-05-26 | 2026-02-20 |  | Overdue | 30 | 82% | Laura Bennett
MS-1006 | Mains Replacement | Pipe Installation Phase 2 | Cheshire | Medium | 2026-02-08 | 2026-03-07 | 2026-02-10 | 2026-03-10 | Complete | 3 | 100% | Laura Bennett
MS-1007 | Mains Replacement | Pressure Testing | Merseyside | High | 2026-01-16 | 2026-02-28 | 2026-01-16 | 2026-02-28 | Complete | 0 | 100% | James Okafor
MS-1008 | Mains Replacement | Commissioning | Merseyside | High | 2026-02-12 | 2026-05-14 | 2026-02-21 |  | Overdue | 21 | 86% | Sarah Mitchell
MS-1009 | Mains Replacement | Final Inspection | Cheshire | Medium | 2026-03-13 | 2026-04-26 | 2026-03-18 | 2026-04-27 | Complete | 1 | 100% | Sarah Mitchell
MS-1010 | Mains Replacement | Handover and Close | Cumbria | High | 2026-02-23 | 2026-04-17 | 2026-02-23 | 2026-04-18 | Complete | 1 | 100% | Laura Bennett
MS-1011 | Mains Replacement | As-Built Drawing Submission | Cumbria | Low | 2026-05-17 | 2026-06-20 | 2026-05-22 |  | On Track | -2 | 68% | Tom Davies
MS-1012 | Mains Replacement | Post-Project Review | Merseyside | Low | 2026-02-17 | 2026-04-16 | 2026-02-20 | 2026-04-11 | Complete | -5 | 100% | James Okafor
MS-1013 | Mains Replacement | Environmental Sign-Off | Merseyside | Medium | 2026-04-13 | 2026-06-09 | 2026-04-17 |  | At Risk | 8 | 58% | James Okafor
MS-1014 | Mains Replacement | Safety Audit Passed | Cumbria | Medium | 2026-02-10 | 2026-03-05 | 2026-02-11 | 2026-03-08 | Complete | 3 | 100% | James Okafor
MS-1015 | Mains Replacement | Client Sign-Off | Lancashire | Medium | 2026-05-20 | 2026-07-10 | 2026-05-21 |  | On Track | 5 | 44% | Sarah Mitchell
MS-1016 | Mains Replacement | Data Quality Check | Greater Manchester | Medium | 2026-04-17 | 2026-06-03 | 2026-04-25 |  | At Risk | 11 | 67% | Tom Davies
MS-1017 | Mains Replacement | Financial Close | Cheshire | Medium | 2026-05-10 | 2026-07-10 | 2026-05-14 |  | On Track | -4 | 51% | Tom Davies
MS-1018 | Mains Replacement | Lessons Learned Capture | Cheshire | Medium | 2026-05-16 | 2026-07-06 | 2026-05-21 |  | On Track | -2 | 59% | James Okafor
MS-1019 | Mains Replacement | Asset Register Update | Greater Manchester | High | 2026-02-19 | 2026-05-06 | 2026-02-22 |  | Overdue | 34 | 79% | Tom Davies
MS-1020 | Mains Replacement | Programme Board Approval | Cumbria | Medium | 2026-04-23 | 2026-07-03 | 2026-04-23 |  | On Track | 3 | 58% | Laura Bennett
MS-1021 | Wastewater Treatment | Baseline Assessment | Greater Manchester | Low | 2025-12-05 | 2026-01-04 | 2025-12-08 | 2026-01-03 | Complete | -1 | 100% | James Okafor
MS-1022 | Wastewater Treatment | Consent Application Submitted | Merseyside | Medium | 2026-05-11 | 2026-07-30 | 2026-05-16 |  | On Track | 4 | 68% | Priya Sharma
MS-1023 | Wastewater Treatment | Regulatory Approval Received | Cumbria | High | 2026-02-18 | 2026-03-04 | 2026-02-23 | 2026-03-04 | Complete | 0 | 100% | James Okafor
MS-1024 | Wastewater Treatment | Contractor Mobilisation | Cumbria | Medium | 2026-03-18 | 2026-05-07 | 2026-03-24 |  | Overdue | 24 | 83% | Sarah Mitchell
MS-1025 | Wastewater Treatment | Civil Works Phase 1 | Lancashire | Medium | 2026-01-29 | 2026-03-18 | 2026-01-30 | 2026-03-13 | Complete | -5 | 100% | James Okafor
MS-1026 | Wastewater Treatment | Civil Works Phase 2 | Greater Manchester | Medium | 2026-04-18 | 2026-06-15 | 2026-04-28 |  | At Risk | 11 | 63% | Laura Bennett
MS-1027 | Wastewater Treatment | M and E Installation | Cheshire | High | 2026-04-23 | 2026-06-12 | 2026-04-30 |  | At Risk | 11 | 78% | Priya Sharma
MS-1028 | Wastewater Treatment | Process Testing | Cumbria | Medium | 2026-01-19 | 2026-02-04 | 2026-01-19 | 2026-02-05 | Complete | 1 | 100% | Laura Bennett
MS-1029 | Wastewater Treatment | Effluent Quality Testing | Cheshire | Medium | 2026-02-02 | 2026-05-06 | 2026-02-11 |  | Overdue | 28 | 76% | Tom Davies
MS-1030 | Wastewater Treatment | Performance Verification | Merseyside | Medium | 2026-03-01 | 2026-04-13 | 2026-03-03 | 2026-04-10 | Complete | -3 | 100% | Tom Davies
MS-1031 | Wastewater Treatment | Operator Training | Merseyside | Medium | 2026-05-06 | 2026-08-01 | 2026-05-07 |  | On Track | 0 | 56% | Tom Davies
MS-1032 | Wastewater Treatment | Handover to Operations | Lancashire | Medium | 2026-04-16 | 2026-06-14 | 2026-04-25 |  | At Risk | 10 | 70% | James Okafor
MS-1033 | Wastewater Treatment | Compliance Report Submitted | Cheshire | High | 2026-01-25 | 2026-02-23 | 2026-01-28 | 2026-02-26 | Complete | 3 | 100% | Priya Sharma
MS-1034 | Wastewater Treatment | Asset Data Loaded | Cumbria | High | 2026-05-21 | 2026-07-08 | 2026-05-26 |  | On Track | -5 | 74% | Laura Bennett
MS-1035 | Wastewater Treatment | Close Out Meeting | Greater Manchester | High | 2026-05-10 | 2026-07-03 | 2026-05-11 |  | On Track | -3 | 43% | Sarah Mitchell
MS-1036 | Wastewater Treatment | Budget Reconciliation | Greater Manchester | High | 2026-05-07 | 2026-07-01 | 2026-05-11 |  | On Track | -1 | 50% | Tom Davies
MS-1037 | Wastewater Treatment | Stakeholder Sign-Off | Merseyside | Medium | 2025-12-21 | 2026-01-16 | 2025-12-21 | 2026-01-18 | Complete | 2 | 100% | Priya Sharma
MS-1038 | Wastewater Treatment | Environmental Audit | Lancashire | High | 2026-03-11 | 2026-05-26 | 2026-03-19 |  | Overdue | 22 | 94% | Priya Sharma
MS-1039 | Wastewater Treatment | Risk Register Updated | Merseyside | High | 2026-02-10 | 2026-05-11 | 2026-02-11 |  | Overdue | 17 | 93% | James Okafor
MS-1040 | Wastewater Treatment | Final Programme Report | Merseyside | Low | 2026-05-11 | 2026-06-03 | 2026-05-20 |  | At Risk | 10 | 66% | Laura Bennett
MS-1041 | Network Monitoring | Sensor Specification Agreed | Greater Manchester | High | 2026-05-08 | 2026-06-08 | 2026-05-11 |  | At Risk | 15 | 80% | Priya Sharma
MS-1042 | Network Monitoring | Procurement Issued | Lancashire | High | 2025-12-30 | 2026-01-20 | 2025-12-31 | 2026-01-22 | Complete | 2 | 100% | James Okafor
MS-1043 | Network Monitoring | Suppliers Selected | Lancashire | High | 2026-04-24 | 2026-07-30 | 2026-04-24 |  | On Track | -2 | 68% | James Okafor
MS-1044 | Network Monitoring | Hardware Delivered | Cumbria | Low | 2025-12-25 | 2026-02-05 | 2025-12-27 | 2026-02-04 | Complete | -1 | 100% | Sarah Mitchell
MS-1045 | Network Monitoring | Installation Phase 1 | Cheshire | Medium | 2026-05-01 | 2026-06-03 | 2026-05-08 |  | At Risk | 10 | 59% | Laura Bennett
MS-1046 | Network Monitoring | Installation Phase 2 | Cheshire | Medium | 2026-05-14 | 2026-06-24 | 2026-05-17 |  | On Track | 1 | 44% | James Okafor
MS-1047 | Network Monitoring | Data Integration Testing | Cheshire | Medium | 2026-04-22 | 2026-06-08 | 2026-04-30 |  | At Risk | 15 | 80% | Priya Sharma
MS-1048 | Network Monitoring | Live Data Verified | Cumbria | Medium | 2026-05-06 | 2026-06-11 | 2026-05-11 |  | At Risk | 5 | 79% | Tom Davies
MS-1049 | Network Monitoring | Dashboard Deployed | Greater Manchester | High | 2026-04-21 | 2026-06-15 | 2026-04-27 |  | At Risk | 10 | 71% | James Okafor
MS-1050 | Network Monitoring | Alarm Thresholds Set | Cheshire | Medium | 2026-01-11 | 2026-02-10 | 2026-01-12 | 2026-02-14 | Complete | 4 | 100% | Sarah Mitchell
MS-1051 | Network Monitoring | Staff Training Complete | Cumbria | High | 2026-04-13 | 2026-06-03 | 2026-04-19 |  | At Risk | 9 | 60% | Priya Sharma
MS-1052 | Network Monitoring | Go-Live Sign-Off | Cheshire | Low | 2026-01-19 | 2026-03-01 | 2026-01-20 | 2026-02-24 | Complete | -5 | 100% | Tom Davies
MS-1053 | Network Monitoring | Performance Review Week 4 | Greater Manchester | High | 2026-05-21 | 2026-06-27 | 2026-05-25 |  | On Track | -2 | 61% | Tom Davies
MS-1054 | Network Monitoring | Performance Review Month 3 | Lancashire | Medium | 2026-05-11 | 2026-06-08 | 2026-05-16 |  | At Risk | 12 | 78% | James Okafor
MS-1055 | Network Monitoring | Optimisation Report | Merseyside | High | 2026-02-08 | 2026-05-25 | 2026-02-14 |  | Overdue | 22 | 95% | Tom Davies
MS-1056 | Network Monitoring | Coverage Audit | Lancashire | Low | 2026-02-05 | 2026-05-21 | 2026-02-07 |  | Overdue | 26 | 75% | Laura Bennett
MS-1057 | Network Monitoring | Data Quality Baseline Set | Greater Manchester | Medium | 2026-03-04 | 2026-04-02 | 2026-03-08 | 2026-03-31 | Complete | -2 | 100% | Laura Bennett
MS-1058 | Network Monitoring | Integration Sign-Off | Lancashire | Medium | 2026-05-11 | 2026-06-06 | 2026-05-18 |  | At Risk | 15 | 79% | Tom Davies
MS-1059 | Network Monitoring | Annual Review | Greater Manchester | High | 2026-03-22 | 2026-05-15 | 2026-03-22 | 2026-05-10 | Complete | -5 | 100% | Priya Sharma
MS-1060 | Network Monitoring | Programme Closure | Merseyside | Medium | 2025-12-06 | 2025-12-23 | 2025-12-11 | 2025-12-22 | Complete | -1 | 100% | Priya Sharma
MS-1061 | Leakage Reduction | District Metering Survey | Cumbria | High | 2026-01-20 | 2026-03-08 | 2026-01-22 | 2026-03-06 | Complete | -2 | 100% | James Okafor
MS-1062 | Leakage Reduction | Pressure Management Review | Cumbria | High | 2026-05-11 | 2026-06-26 | 2026-05-16 |  | On Track | -1 | 73% | Tom Davies
MS-1063 | Leakage Reduction | Intervention Plan Agreed | Merseyside | Low | 2025-12-04 | 2025-12-19 | 2025-12-06 | 2025-12-17 | Complete | -2 | 100% | Sarah Mitchell
MS-1064 | Leakage Reduction | Repair Works Phase 1 | Lancashire | High | 2026-05-23 | 2026-07-09 | 2026-05-25 |  | On Track | 1 | 55% | Sarah Mitchell
MS-1065 | Leakage Reduction | Repair Works Phase 2 | Cumbria | Low | 2026-03-31 | 2026-04-25 | 2026-04-01 | 2026-04-23 | Complete | -2 | 100% | Priya Sharma
MS-1066 | Leakage Reduction | Pressure Reduction Installed | Greater Manchester | High | 2026-01-11 | 2026-01-25 | 2026-01-14 | 2026-01-21 | Complete | -4 | 100% | Priya Sharma
MS-1067 | Leakage Reduction | Meter Installation | Cumbria | Medium | 2026-05-10 | 2026-07-22 | 2026-05-13 |  | On Track | 3 | 56% | Sarah Mitchell
MS-1068 | Leakage Reduction | Night Flow Monitoring Live | Cumbria | Medium | 2026-05-07 | 2026-07-02 | 2026-05-07 |  | On Track | -5 | 54% | Laura Bennett
MS-1069 | Leakage Reduction | First Month Performance Report | Merseyside | High | 2026-02-28 | 2026-04-02 | 2026-03-04 | 2026-04-06 | Complete | 4 | 100% | Tom Davies
MS-1070 | Leakage Reduction | Quarter 1 Leakage Report | Greater Manchester | High | 2026-03-06 | 2026-05-12 | 2026-03-06 |  | Overdue | 26 | 72% | Sarah Mitchell
MS-1071 | Leakage Reduction | Quarter 2 Leakage Report | Lancashire | High | 2026-05-08 | 2026-08-01 | 2026-05-11 |  | On Track | 1 | 60% | Laura Bennett
MS-1072 | Leakage Reduction | Regulatory Return Filed | Merseyside | High | 2026-02-28 | 2026-05-25 | 2026-03-04 |  | Overdue | 35 | 94% | Laura Bennett
MS-1073 | Leakage Reduction | Target Verification | Cheshire | High | 2026-05-09 | 2026-07-18 | 2026-05-11 |  | On Track | 4 | 45% | Laura Bennett
MS-1074 | Leakage Reduction | Scheme Completion Report | Greater Manchester | Low | 2026-01-12 | 2026-02-03 | 2026-01-15 | 2026-02-01 | Complete | -2 | 100% | Laura Bennett
MS-1075 | Leakage Reduction | Stakeholder Communication | Merseyside | High | 2026-04-01 | 2026-04-22 | 2026-04-03 | 2026-04-20 | Complete | -2 | 100% | Sarah Mitchell
MS-1076 | Leakage Reduction | Lessons Learned | Merseyside | Medium | 2026-04-27 | 2026-07-05 | 2026-04-28 |  | On Track | -3 | 58% | Sarah Mitchell
MS-1077 | Leakage Reduction | Asset Update | Cheshire | Medium | 2026-04-27 | 2026-06-28 | 2026-04-30 |  | On Track | 1 | 46% | Laura Bennett
MS-1078 | Leakage Reduction | Technical Review | Lancashire | High | 2026-05-15 | 2026-06-27 | 2026-05-17 |  | On Track | -4 | 42% | Priya Sharma
MS-1079 | Leakage Reduction | Cost Benefit Analysis | Merseyside | Low | 2026-05-11 | 2026-06-25 | 2026-05-13 |  | On Track | 4 | 70% | Priya Sharma
MS-1080 | Leakage Reduction | Programme Sign-Off | Greater Manchester | Medium | 2026-05-15 | 2026-07-19 | 2026-05-17 |  | On Track | 5 | 51% | James Okafor