## Risk_Register
Risk_ID | Date_Raised | Workstream | Region | Risk_Description | Risk_Category | Likelihood_1_5 | Impact_1_5 | Risk_Score | RAG_Status | Milestones_Affected | Owner | Mitigation_Action | Target_Resolution | Current_Status | Last_Updated
RSK-101 | 2024-10-30 | Wastewater Treatment | Cumbria | Incomplete asset records in CEC system causing reporting gaps | Data Quality | 4 | 5 | 20 | Red | 4 | Sarah Mitchell | Conduct full data audit and implement mandatory field validation rule | 2025-01-22 | Open | 2024-12-14
RSK-102 | 2024-09-06 | Network Monitoring | Greater Manchester | Contractor reporting portal submission delays affecting weekly MI | Programme Delivery | 3 | 4 | 12 | Amber | 2 | Laura Bennett | Escalate to programme director and agree remediation timeline with contractor | 2024-10-16 | Open | 2024-10-09
RSK-103 | 2025-02-19 | Network Monitoring | Greater Manchester | GIS mapping data inconsistencies across regional boundaries | Data Quality | 3 | 3 | 9 | Amber | 6 | James Okafor | Commission boundary reconciliation exercise with GIS team | 2025-06-12 | Open | 2025-04-04
RSK-104 | 2024-04-30 | Leakage Reduction | Lancashire | SCADA data feed latency exceeding 24-hour SLA | Technical | 3 | 4 | 12 | Amber | 4 | Laura Bennett | Raise P1 incident with IT and implement buffer storage solution | 2024-06-30 | Open | 2024-05-06
RSK-105 | 2024-04-29 | Wastewater Treatment | Cheshire | SAP Finance system integration producing duplicate transactions | Data Quality | 4 | 4 | 16 | Red | 6 | Sarah Mitchell | Engage SAP support team and implement transaction deduplication logic | 2024-07-07 | Closed | 2024-06-11
RSK-106 | 2025-03-29 | Leakage Reduction | Cumbria | Skilled data analyst resource shortage on Mains Replacement workstream | Resource | 3 | 3 | 9 | Amber | 1 | Laura Bennett | Initiate recruitment and interim resource request to PMO | 2025-05-15 | Open | 2025-05-13
RSK-107 | 2024-12-21 | Network Monitoring | Cheshire | Regulatory reporting deadline at risk due to data completeness issues | Regulatory | 4 | 5 | 20 | Red | 3 | Sarah Mitchell | Implement daily data completeness check and escalation protocol | 2025-02-22 | Open | 2025-01-01
RSK-108 | 2024-09-19 | Network Monitoring | Lancashire | Stakeholder misalignment on KPI definitions across workstreams | Stakeholder | 3 | 3 | 9 | Amber | 5 | Sarah Mitchell | Facilitate KPI alignment workshop with all workstream leads | 2024-12-12 | Open | 2024-10-07
RSK-109 | 2024-12-11 | Leakage Reduction | Lancashire | Weather disruption to Cumbria field operations affecting schedule | Programme Delivery | 2 | 4 | 8 | Amber | 3 | James Okafor | Review programme float and identify alternative resource options | 2025-03-09 | Open | 2025-01-13
RSK-110 | 2024-10-06 | Mains Replacement | Merseyside | Manual data entry errors in Contractor Reporting Portal | Data Quality | 4 | 3 | 12 | Amber | 1 | Laura Bennett | Implement data entry validation and introduce checker role | 2024-11-25 | In Progress | 2024-10-23
RSK-111 | 2024-04-02 | Mains Replacement | Greater Manchester | Third-party supplier unable to meet BIM data delivery standard | Technical | 3 | 4 | 12 | Amber | 1 | Priya Sharma | Review supplier contract and identify alternative data delivery route | 2024-05-07 | Open | 2024-05-27
RSK-112 | 2024-10-14 | Leakage Reduction | Merseyside | Scope creep on Wastewater Treatment Phase 2 increasing data volume | Programme Delivery | 3 | 3 | 9 | Amber | 1 | Priya Sharma | Raise change request and update programme schedule accordingly | 2024-12-02 | In Progress | 2024-10-26
RSK-113 | 2024-08-06 | Network Monitoring | Cheshire | Legacy system migration risk — data loss during transfer | Technical | 2 | 5 | 10 | Amber | 6 | Laura Bennett | Implement pre-migration data snapshot and validation protocol | 2024-10-28 | Open | 2024-10-04
RSK-114 | 2024-10-08 | Wastewater Treatment | Merseyside | Insufficient audit trail for data changes in asset register | Regulatory | 3 | 4 | 12 | Amber | 6 | Laura Bennett | Define audit trail requirements and implement logging in system | 2024-11-22 | Open | 2024-11-10
RSK-115 | 2024-04-24 | Network Monitoring | Cumbria | Network Monitoring sensor failure rate exceeding 5% threshold | Technical | 3 | 3 | 9 | Amber | 4 | Sarah Mitchell | Agree maintenance schedule and failure response SLA with supplier | 2024-07-14 | Open | 2024-04-29
RSK-116 | 2025-01-09 | Network Monitoring | Lancashire | Leakage reduction targets at risk due to reporting methodology change | Regulatory | 3 | 4 | 12 | Amber | 3 | Priya Sharma | Engage Ofwat relationship manager and document methodology change | 2025-04-07 | Open | 2025-01-10
RSK-117 | 2025-04-14 | Leakage Reduction | Merseyside | Cross-workstream data lineage gaps causing reconciliation failures | Data Quality | 4 | 4 | 16 | Red | 4 | Laura Bennett | Map data lineage across all workstreams and document in data dictionary | 2025-08-01 | Open | 2025-04-30
RSK-118 | 2025-04-25 | Mains Replacement | Merseyside | Pressure on resource capacity during Q4 regulatory return period | Resource | 4 | 4 | 16 | Red | 1 | Laura Bennett | Resource plan for Q4 and agree priority MI outputs with CCI heads | 2025-06-25 | In Progress | 2025-05-05
RSK-119 | 2024-09-25 | Network Monitoring | Cheshire | Inconsistent milestone status definitions between workstream leads | Stakeholder | 3 | 3 | 9 | Amber | 6 | Tom Davies | Issue updated milestone status guidance and embed in governance framework | 2025-01-14 | Open | 2024-11-18
RSK-120 | 2025-04-13 | Wastewater Treatment | Greater Manchester | Dashboard performance degradation due to data volume growth | Technical | 2 | 3 | 6 | Green | 2 | Tom Davies | Optimise data model and implement incremental refresh in Power BI | 2025-06-21 | In Progress | 2025-04-20
RSK-121 | 2024-05-01 | Mains Replacement | Merseyside | Change control process not followed for information model updates | Regulatory | 3 | 4 | 12 | Amber | 3 | Laura Bennett | Retrain team on change control process and audit recent changes | 2024-06-18 | Open | 2024-06-16
RSK-122 | 2024-10-29 | Mains Replacement | Lancashire | Contractor data submissions not meeting agreed format standards | Data Quality | 4 | 3 | 12 | Amber | 3 | Sarah Mitchell | Issue data format guidance and implement automated format validation | 2025-02-25 | In Progress | 2024-12-26
RSK-123 | 2024-12-15 | Mains Replacement | Greater Manchester | Delay to Merseyside site access affecting milestone programme | Programme Delivery | 3 | 4 | 12 | Amber | 4 | James Okafor | Engage landowner and explore alternative access route options | 2025-01-31 | Open | 2025-01-25
RSK-124 | 2024-07-31 | Network Monitoring | Cumbria | Power BI licence availability limiting reporting access for CCI heads | Resource | 2 | 3 | 6 | Green | 3 | Tom Davies | Submit licence review request and identify shared access solution | 2024-10-06 | In Progress | 2024-08-17
RSK-125 | 2024-08-18 | Mains Replacement | Merseyside | Missing traceability between asset IDs and programme milestones | Data Quality | 4 | 4 | 16 | Red | 2 | Sarah Mitchell | Create asset-to-milestone mapping table and validate with data owners | 2024-10-16 | Open | 2024-08-23